## Calorimetry
R&D Technology | Participating Institutes | Description/ Concept | Milestones | Future Activities / Priorities
SDHCAL uM | LAPP | Use of Micromegas intrinsic high-rate capability and proportionality | 2006-2009
|  | to improve the energy measurement and the calorimeter calibration. | Small single-layer Micromegas prototypes
with external electronics for characterisation of
Micromegas for calorimetry: Landau distributions,
voltage and P/T dependence of signal
2009-2012
* Development of Active Sensor Unit
PCB with integrated asic, anode pads and bulk mesh.
* MICROROC ASIC for ILC: selft-trigger + power-pulsing + 2-bit RO
* Construction of 4 prototypes of 1x1 m2
and beam-test in the SDHCAL structure with 46 RPCs layers
2012-2013
* Study of different resistive configurations to suppress sparking (ANR SPLAM)
* Test in e-beam of 3 prototypes with integrated ASIC, show charge-up effect and spark suppression
| +Institute of Nuclear and Particle Physics, Demokritos |  | 2014-2015
| +CEA Saclay |  | * Systematic study of a resistive configuration for spark suppression and high rate capability
* Vary the RC-constant with 6 small prototypes with external electronics
* Rate capability and in-beam spark study to determine the optimal RC
| +Weizmann |  |  | 2016-2017
Implement the best resistive configuration on an ASU (with integrated ASIC)
Build several layers, number depending on funding
If sufficient number of layers, build and operate a small calorimeter prototype
equipped with resistive Micromegas and possibly also THGEM-based elements.
Full characterisation in-beam of Micromegas calorimetry:
response, resolution, profiles, multi-threshold compensation, MC validation.